## Sheet 1
Table 1
# file wbs.csv
pja 02-27-2017 orig
gantt chart for jad table parser
task | duration in days (done in green) |  | Mon | Tues | wed | This | fri | Sat | sun
set up git hub | 1 | day | 27 | 28 | 1 | 2 | 3 | 4 | 5
set up gantt (this file) | 1 | tasks | git hub - wbs - begin JadP | o2-design JadP in basii convert getKeys:- getKeyData | — | **02 | **02 | add each paragraph in JadP as 1 day task
design data flow diagram | 2 |  | Mon | Tues | wed | This | fri | Sat | sun
design ops manual |  | 2017-03-01 | 6 | 7 | 8 | 9 | 10 | 11 | 12
design parser JadP in basii
add each paragraph as 1 day task
design ndsSave in BASII
design ndsLoad in BASII
design ndsGet in BASII
jadT :-def jadT(): | CODED
doTable :-def doTable(): | CODED
table2 :-def table2(): | CODED
getKeys :- | CODED
getKeyData :- | CODED
getFK :- /* of t.c {( t.c = v )} */
getFK2 :-
gfk3 :-
getTags :- "(" na ''' /* , ) ; */
getTagData :-
getTagFK :- /* of t.c {( t.c = v )}
getTagFK2 :-
gfkT3 :-